## RELEASE METRICS
Product Team >> | CarePricer |  |  | Contract Manager |  |  | Web PDI |  |  | CDM Manager |  |  | Content Legacy |  |  | KnowledgeSource |  |  | Reporting
RELEASE NAME | 15.2 | 15.3 | 15.4 | 15.2 | 15.3 | 15.4 | 15.2 | 15.3 | 15.4 | 3.9.3 | 3.9.4 | 3.9.5 | 2.8 | 2.9 | 2.1 | 4.9.8 | 4.9.9 | 4.9.10 | 15.2 | 15.3 | 15.4
RELEASE - PLANNED START DATE | 2015-01-14 | 2015-05-06 | 2015-10-10 | 2015-01-14 | 2015-05-06 | 2015-10-10 | 2015-03-18 | 2015-07-03 | 2015-09-23 | 2014-10-29 | 2015-04-14 | 2015-09-01 | 2014-10-16 | 2015-04-30 | 2015-09-03 | 2014-10-28 | 2015-04-16 | 2015-09-01 | 2014-11-13 | 2015-03-19 | 2015-07-10
RELEASE - ACTUAL START DATE | 2015-01-14 | 2015-05-06 | 2015-10-10 | 2015-01-14 | 2015-05-06 | 2015-10-10 | 2015-03-18 | 2015-06-24 | 2015-09-23 | 2014-10-29 | 2015-04-14 | 2015-09-01 | 2014-10-16 | 2015-04-30 | 2015-09-03 | 2014-10-28 | 2015-04-16 | 2015-09-01 | 2014-11-13 | 2015-03-19 | 2015-07-10
COMMITTED RELEASE DATE | 2015-06-12 | 2015-10-09 | 2016-01-22 | 2015-06-12 | 2015-10-09 | TBD | 2015-06-24 | 2015-09-22 | 2015-12-11 | 2015-04-30 | 2015-08-31 | TBD | 2015-04-30 | 2015-08-19 | TBD | 2015-04-30 | 2015-08-31 | TBD | 2015-03-19 | 2015-07-09 | 2015-10-29
ACTUAL RELEASE DATE | 2015-06-12 | 2015-10-09 |  | 2015-06-12 | 2015-10-09 |  | 2015-06-24 | 2015-09-22 |  | 2015-04-30 |  |  | 2015-04-30 |  |  | 2015-04-30 |  |  | 2015-03-19 | 2015-07-09
STORY POINTS - COMMITTED IN RELEASE PLANNING | NA | NA |  | 318 | 332 |  | 161 | 142 |  | 317 | 314 |  | 498 | 306 |  | 417 | 354 |  | 464 | 344 | 400
STORY POINTS - DELIVERED AS AGAINST RELEASE SCOPE | NA |  |  | 318 |  |  | 161 |  |  | 317 |  |  | 498 |  |  | 417 | 351 |  | 464 | 344
STORY POINTS - ACCEPTED AT THE END OF RELEASE | 357 |  |  | 394 |  |  | 161 |  |  | 317 |  |  | 498 |  |  | 417 | 351 |  | 459 | 345
Schedule Accuracy - Target (in %) | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% | +/-15%
Schedule Accuracy- Actual (in %) | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | -30394% |  | 0% | -38050% |  | 0% | -30837% |  | 0% | 0% | -38114%
Delivered vs Planned Story Points - Target (in %) | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% |  | +/-15% | +/-15% | +/-15%
Delivered vs Planned Story Points - Actual (in %) | NA |  |  | 123.9% | 0% |  | 100% | 0% |  | 100% | 0% |  | 100% | 0% |  | 100% | 99.15% |  | -1% | 100.3% | 0%
% Original Release Scope - Target | NA | NA |  | NA | NA |  | NA | NA |  | NA | NA |  | NA | NA |  | NA | NA |  | NA | NA | NA
% Original Release Scope - Actual | NA |  |  | 100% | 0% |  | 100% | 0% |  | 100% | 0% |  | 100% | 0% |  | 100% | 99.15% |  | 100% | 100% | 0%
Critical/High Defects found within 30 days - Target | <4 | <4 |  | <4 | <4 |  | <4 | <4 |  | <4 | <4 |  | <4 | <4 |  | <4 | <4 |  | <4 | <4 | <4
CRITICAL/HIGH DEFECTS FOUND WITHIN 30 DAYS - ACTUAL | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 1 |  |  | 0 | 0
NO OF BCIs REPORTED - Target | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
NO OF BCIs REPORTED - Actual | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 1 | 0 |  | 1 | 0 |  | 0 | 0
NO OF BCIs by BANAGLORE team - Actual | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 0 |  |  | 0 | 0
NO OF UNPLANNED RELEASES (HOTFIXES & HOT UPDATES) | 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1 |  |  | 0 |  |  | 0 | 0
Note on C2: Current release
Note on D2: Current release
Note on F2: Current release
Note on G2: Current release
Note on I2: Current release
Note on J2: Current release
Note on M2: Current release
Note on P2: Current release
Note on S2: Current release
Note on V2: Current release
Note on B7: Story points are not estimated at release level and at sprint level these are added into Rally
Note on C7: Story points are not estimated at release level and at sprint level these are added into Rally
Note on B8: Story points are not estimated at release level and at sprint level these are added into Rally
Note on A14: MedAssets is in the process of benchmarking target. We need to check on this.
Note on A21: Report “hotfixes” and “hot updates” (reprioritized client- requested enhancements). Target 10% YoY reduction.

## PAS
Release Name | Sprint Type | Sprint Number | Sprint Start Date | Sprint End Date | Actual Capacity (in Hrs) | INITIAL VELOCITY PLANNED | Story Points Added | Story Points Removed | FINAL VELOCITY PLANNED | ACTUAL VELOCITY | Story Points Carried Over | Regression Defects with Severity | REQUIREMENTS VOLATILITY (in %) | SPRINT ACCEPTANCE (in %) | Remarks
15.3 | DEVELOPMENT | 2015_21 | 2015-10-07 | 2015-10-20 | 471 | 39 | 0 | 0 | 39 | 39 | 13 | NA | 0% | 100% | NA
15.3 | DEVELOPMENT | 2015_22 | 2015-10-21 | 2015-11-03 | 387 | 44 | 0 | 0 | 44 | 44 | 13 | NA | 0% | 100% | NA
15.3 | DEVELOPMENT | 2015_23 | 2015-11-04 | 2015-11-17 | 405 | 23 | 0 | 0 | 23 | 23 | 0 | NA | 0% | 100% | NA
15.3 | DEVELOPMENT | 2015_24 | 2015-11-18 | 2015-12-01 | 504 | 23 | 0 | 0 | 23 | 23 | 0 | NA | 0% | 100% | NA
15.3 | DEVELOPMENT | 2015_25 | 2015-12-02 | 2015-12-15 | 459 | 11 | 0 | 0 | 11 | 5 | 6 | NA | 0% | 45.45% | due to VDi network and Environment issue
15.3 | DEVELOPMENT | 2015_26 | 2015-12-16 | 2015-12-29 | 486 | 19 | 0 | 0 | 19 | 16 | 3 | NA | 0% | 84.21% | Scope Change
16.1 | DEVELOPMENT | 2016_01 | 2015-12-30 | 2016-01-12 | 423 | 10 | 0 | 0 | 10 | 10 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 2016_02 | 2016-01-13 | 2016-01-25 | 307 | 31 | 0 | 0 | 31 | 31 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 2016_03 | 2016-01-27 | 2016-02-09 | 540 | 18 | 0 | 0 | 18 | 18 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 2016_04 | 2016-02-10 | 2016-02-23 | 504 | 15 | 0 | 0 | 15 | 15 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 2016_05 | 2016-02-24 | 2016-03-08 | 504 | 42 | 0 | 0 | 42 | 42 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 2016_06 | 2016-03-09 | 2016-03-22 | 504 | 23 | 0 | 0 | 23 | 23 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 2016_07 | 2016-03-22 | 2016-04-05 | 504 | 31 | 0 | 0 | 31 | 31 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 2016_08 | 2016-04-06 | 2016-04-19 | 522 | 28 | 0 | 0 | 28 | 28 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 2016_09 | 2016-04-20 | 2016-05-03 | 414 | 34 | 0 | 0 | 34 | 34 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 2016_10 | 2016-05-04 | 2016-05-17 | 307 | 70 | 0 | 0 | 70 | 0 | 70 | NA | 0% | 0% | Due to bugs in Fav.Service & Fav.Case
16.1 | DEVELOPMENT | 2016_11 | 2016-05-18 | 2016-05-31 | 540 | 142 | 0 | 0 | 142 | 106 | 36 | NA | 0% | 74.65% | QA validation was pending
16.1 | DEVELOPMENT | 2016_12 | 2016-06-01 | 2016-06-14 | 504 | 89 | 0 | 0 | 89 | 65 | 24 | NA | 0% | 73.03% | QA validation was pending
16.1 | DEVELOPMENT | 2016_13 | 2016-06-15 | 2016-06-28 | 504 | 108 | 0 | 0 | 108 | 72 | 36 | NA | 0% | 66.67% | QA validation was pending
16.1 | DEVELOPMENT | 2016_14 | 2016-06-29 | 2016-07-12 | 504 | 125 | 0 | 0 | 125 | 66 | 59 | NA | 0% | 52.8% | QA validation was pending
16.1 | DEVELOPMENT | 2016_15 | 2016-07-13 | 2016-07-26 | 522 | 116 | 0 | 0 | 116 | 59 | 57 | NA | 0% | 50.86% | 2 PBI's QA validation was pending and for other PBI's dev was In-Progress

## CarePricer
Release Name | Sprint Type | Sprint Number | Sprint Start Date | Sprint End Date | Actual Capacity (in Hrs) | INITIAL VELOCITY PLANNED | Story Points Added | Story Points Removed | FINAL VELOCITY PLANNED | ACTUAL VELOCITY | Story Points Carried Over | Regression Defects with Severity | REQUIREMENTS VOLATILITY (in %) | SPRINT ACCEPTANCE (in %) | Remarks
15.3 | DEVELOPMENT | 2015_10 | 2015-05-06 | 2015-05-20 | 526 | 61 | 0 | 0 | 61 | 48 | 13 | NA | 0% | 78.69% | Scope changed in the middle.
15.3 | DEVELOPMENT | 2015_11 | 2015-05-20 | 2015-06-03 | 486 | 59 | 0 | 0 | 59 | 35 | 24 | NA | 0% | 59.32% | Team was working on production issues
15.3 | DEVELOPMENT | 2015_12 | 2015-06-03 | 2015-06-16 | 651 | 86 | 0 | 0 | 86 | 55 | 31 | NA | 0% | 63.95% | Team was working on performance issue which was encountered during 15.2 release
15.3 | DEVELOPMENT | 2015_13 | 2015-06-17 | 2015-06-30 | 575 | 70 | 0 | 0 | 70 | 44 | 26 | NA | 0% | 62.86% | Performance LAB was not available, Research took longer time
15.3 | DEVELOPMENT | 2015_14 | 2015-07-01 | 2015-07-14 | 638 | 58 | 11 | 0 | 69 | 61 | 8 | NA | 18.97% | 88.41% | CPC standardization work was taken more
15.3 | DEVELOPMENT | 2015_15 | 2015-07-15 | 2015-07-28 | 523 | 52 | 0 | 0 | 52 | 39 | 13 | NA | 0% | 75% | Due to unplanned PTOs
15.3 | DEVELOPMENT | 2015_16 | 2015-07-29 | 2015-08-11 | 511 | 66 | 10 | 0 | 76 | 58 | 18 | NA | 15.15% | 76.32% | Due to priority chnages at last minute
15.3 | DEVELOPMENT | 2015_17 | 2015-08-12 | 2015-08-25 | 416 | 55 | 8 | 0 | 63 | 58 | 13 | NA | 14.55% | 92.06% | Due to ICD10 Priority chnages in mid of iteration
15.3 | DEVELOPMENT | 2015_18 | 2015-08-26 | 2015-09-08 | 442 | 44 | 0 | 0 | 44 | 36 | 8 | NA | 0% | 81.82% | Regression prep and test cases has been carried over
15.3 | DEVELOPMENT | 2015_19 | 2015-09-09 | 2015-09-22 | 417 | 53 | 0 | 0 | 53 | 40 | 13 | NA | 0% | 75.47% | Un planned PTO & ICD10 priorities
15.3 | DEVELOPMENT | 2015_20 | 2015-09-23 | 2015-10-06 | 276 | 29 | 0 | 0 | 29 | 13 | 16 | NA | 0% | 44.83% | Bussiness rules has been chnages for ICD10 priorities
15.3.1 | DEVELOPMENT | 2015_21 | 2015-10-07 | 2015-10-20 | 270 | 53 | 0 | 0 | 53 | 53 | 0 | NA | 0% | 100% | Nil
15.3.2 | DEVELOPMENT | 2015_22 | 2015-10-21 | 2015-11-03 | 270 | 41 | 0 | 0 | 41 | 41 | 0 | NA | 0% | 100%
15.3.2 | DEVELOPMENT | 2015_23 | 2015-11-04 | 2015-11-17 | 270 | 48 | 0 | 0 | 48 | 35 | 13 | NA | 0% | 72.92% | Due to technical challenges And Remaining QA
16.1 | DEVELOPMENT | 2015_24 | 2015-11-18 | 2015-12-01 | 336 | 43 | 0 | 0 | 43 | 16 | 27 | NA | 0% | 37.21% | Production issue which was the priority one came into picture. So team concentrated into it which caused 27 pointers carry forwrded.
16.1 | DEVELOPMENT | 2015_25 | 2015-12-02 | 2015-12-15 | 900 | 71 | 0 | 16 | 55 | 39 | 16 | NA | -22.54% | 70.91% | Production issue which was the priority one came into picture. So team concentrated into it which caused 16 pointers carry forwrded.
16.1 | DEVELOPMENT | 2015_26 | 2015-12-16 | 2015-12-29 | 900 | 44 | 0 | 0 | 44 | 24 | 20 | NA | 0% | 54.55% | Regression testing was taken in the iteration-26 +Dev's took the research PBI's which was carry overed.
16.1.1 | DEVELOPMENT | 2016_01 | 2015-12-30 | 2015-01-12 | 280 | 56 | 0 | 0 | 56 | 46 | 5 | NA | 0% | 82.14% | QA activity was pending
16.2 | DEVELOPMENT | 2016_02 | 2016-01-13 | 2016-01-26 | 211 | 48 | 0 | 10 | 38 | 22 | 16 | NA | -20.83% | 57.89% | Some requirement changes was there in PAS related work items so the PSA related items were carry forwarded.
16.2 | DEVELOPMENT | 20016_03 | 2016-01-27 | 2016-02-09 | 273 | 36 | 0 | 0 | 36 | 20 | 16 | NA | 0% | 55.56% | PAS related PBI's requierment was changing so most of the PBI's were carry forwarded
16.2 | DEVELOPMENT | 2016_04 | 2016-02-10 | 2016-02-23 | 280 | 48 | 9 | 0 | 57 | 39 | 18 | N/A | 18.75% | 68.42% | PAS related PBI's carry forwarded
16.2 | DEVELOPMENT | 2016_05 | 2016-02-24 | 2016-03-08 | 364 | 52 | 0 | 0 | 52 | 44 | 8 | N/A | 0% | 84.62% | One PBI was carry forwarded waiting for input from Onshore Account Management team
16.2 | DEVELOPMENT | 2016_06 | 2016-03-09 | 2016-03-22 | 400 | 57 | 0 | 0 | 57 | 26 | 31 | N/A | 0% | 45.61% | Some Pbi's was carry forwarded for testing purpose
16.2 | DEVELOPMENT | 2016-07 | 2016-03-23 | 2016-04-05 | 350 | 65 | 0 | 0 | 65 | 34 | 31 | N/A | 0% | 52% | Some Pbi's was carry forwarded for testing purpose
16.2 | DEVELOPMENT | 2016-08 | 2016-04-06 | 2016-04-19 | 10 | 1 | 0 | 0 | 1 | 1 | 0 | N/A | 0% | 100% | Some priority task came so respective PBI's were carry forwarded
16.3 | DEVELOPMENT | 2016-09 | 2016-04-20 | 2016-05-03 | 30 | 14 | 0 | 0 | 14 | 8 | 6 | N/A | 0% | 57.14% | Some priority task came so respective PBI's were carry forwarded
16.4 | DEVELOPMENT | 2016_10 | 2016-05-04 | 2016-05-17 | 200 | 55 | 0 | 0 | 55 | 29 | 26 | N/A | 0% | 52.73% | Some priority task came so respective PBI's were carry forwarded
16.4 | DEVELOPMENT | 2016_11 | 2016-05-18 | 2016-05-31 | 220 | 50 | 0 | 0 | 50 | 19 | 31 | N/A | 0% | 38% | Some priority items were taken in PAS
Formulas:
Sprint Start Date = [Sprint End Date, row above]+1
Sprint End Date = [Sprint Start Date]+13

## CM
Release Name | Sprint Type | Sprint Number | Sprint Start Date | Sprint End Date | Actual Capacity (in Hrs) | INITIAL VELOCITY PLANNED | Story Points Added | Story Points Removed | FINAL VELOCITY PLANNED | ACTUAL VELOCITY | Story Points Carried Over | Regression Defects with Severity | REQUIREMENTS VOLATILITY (in %) | SPRINT ACCEPTANCE (in %) | Remarks
15.3 | DEVELOPMENT | 2015_10 | 2015-05-06 | 2015-05-20 | 583 | 74 | 0 | 0 | 74 | 61 | 13 | NA | 0% | 82.43% | Found Inline defect by QA on last day, Development finished quite late so QA couldn’t finish the testing.
15.3 | DEVELOPMENT | 2015_11 | 2015-05-20 | 2015-06-03 | 453 | 77 | 0 | 0 | 77 | 35 | 42 | NA | 0% | 45.45% | Complexity and scope changes
15.3 | DEVELOPMENT | 2015_12 | 2015-06-03 | 2015-06-16 | 663 | 102 | 0 | 0 | 102 | 76 | 26 | NA | 0% | 74.51% | QA scope increased, Found 1 inline defect, got technical glitch in 1 item due to dependency with other team Xcollect onshore.
15.3 | DEVELOPMENT | 2015_13 | 2015-06-17 | 2015-06-30 | 656 | 88 | 0 | 0 | 88 | 75 | 13 | NA | 0% | 85.23% | Found 1 machine specific issue while testing
15.3 | DEVELOPMENT | 2015_14 | 2015-07-01 | 2015-07-14 | 557 | 70 | 0 | 0 | 70 | 28 | 42 | NA | 0% | 40% | Inline defects, Scenarios added, technical complexity.
15.3 | DEVELOPMENT | 2015_15 | 2015-07-15 | 2015-07-28 | 757 | 63 | 0 | 0 | 63 | 63 | 0 | NA | 0% | 100%
15.3 | DEVELOPMENT | 2015_16 | 2015-07-29 | 2015-08-11 | 763 | 68 | 0 | 0 | 68 | 68 | 0 | NA | 0% | 100%
15.3 | REGRESSION | 2015_17 | 2015-08-12 | 2015-08-25 | 665 | 55 | 0 | 0 | 55 | 55 | 0 | 0 | 0% | 100%
15.3 | HARDENING | 2015_18 | 2015-08-26 | 2015-09-08 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
16.1 | DEVELOPMENT | 2015_19 | 2015-09-09 | 2015-09-22 | 441 | 26 | 0 | 0 | 26 | 0 | 26 | NA | 0% | 0% | Feature was complex and dealy in response from ICS team
16.1 | DEVELOPMENT | 2015_20 | 2015-09-23 | 2015-10-06 | 350 | 39 | 0 | 0 | 39 | 0 | 0 | NA | 0% | 0%
16.1 | DEVELOPMENT | 2015_21 | 2015-10-07 | 2015-10-20 | 440 | 63 | 0 | 0 | 63 | 45 | 13 | NA | 0% | 71.43% | New development and business clarifications
16.1 | DEVELOPMENT | 2015_22 | 2015-10-21 | 2015-11-03 | 304 | 39 | 0 | 0 | 39 | 26 | 13 | NA | 0% | 66.67% | Build for 13 Ponit story delayed due to Team City Down time, hence carry forwarded
16.1 | DEVELOPMENT | 2015_23 | 2015-11-04 | 2015-11-17 | 550 | 58 | 0 | 0 | 58 | 42 | 16 | NA | 0% | 72.41% | Requirement Clarification
16.1 | DEVELOPMENT | 2015_24 | 2015-11-18 | 2015-12-01 | 450 | 56 | 0 | 0 | 56 | 32 | 24 | NA | 0% | 57.14% | Clarification deplayed due to thanks giving day holidays ad hence PBI's carry forwarded.
16.1 | DEVELOPMENT | 2015_25 | 2015-12-02 | 2015-12-15 | 500 | 48 | 0 | 0 | 48 | 48 | 0 | NA | 0% | 100%
16.1 | Release Prep | 2015_26 | 2015-12-16 | 2015-12-29 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | Release Prep And regression iteration
16.1 | HARDENING | 2016_01 | 2015-12-30 | 2016-01-12 | 370 | 26 | 0 | 0 | 26 | 26 | 0 | 0 | 0% | 100%
16.2 | DEVELOPMENT | 2016_02 | 2016-01-13 | 2016-01-26 | 420 | 39 | 0 | 0 | 39 | 15 | 24 | 0 | 0% | 38.46% | PBI's Carried forwarded due to inline defects and complexity of the feature.
16.2 | DEVELOPMENT | 2016_03 | 2016-01-27 | 2016-02-09 | 430 | 37 | 0 | 0 | 37 | 13 | 24 | 0 | 0% | 35.14% | PBI's Carried forwarded due to inline defects and complexity of the feature.
16.2 | DEVELOPMENT | 2016_04 | 2016-02-10 | 2016-02-23 | 640 | 66 | 0 | 0 | 66 | 8 | 58 | 0 | 12.12% | 12.12% | PBI's Carried forwarded due to inline defects and complexity of the feature and unplanned PTO, one 8 point PBI had requirement volatality and hence had to be carry forwarded.
16.2 | DEVELOPMENT | 2016_05 | 2016-02-24 | 2016-03-08 | 720 | 101 | 0 | 0 | 101 | 101 | 0 | 0 | 0% | 100%
16.2 | Release Prep | 2016_06 | 2016-03-09 | 2016-03-22 | 680 | 0 | 0 | 0 | 0 | 0 | 0 | 2-High | 0% | 0% | Two regression defects identified with High Severity
16.2 | Hardening | 2016_07 | 2016-03-23 | 2016-04-05 | 623 | 0 | 0 | 0 | 0 | 0 | 0 | 1-High | 0% | 0% | One regression defects identified with High Severity
16.3 | DEVELOPMENT | 2016_08 | 2016-04-06 | 2016-04-19 | 630 | 53 | 0 | 0 | 53 | 29 | 24 | N/A | 0% | 54.72% | Items carry over due to inline defects and technical challenge
16.3 | DEVELOPMENT | 2016_09 | 2016-04-20 | 2016-05-03 | 670 | 34 | 0 | 0 | 58 | 45 | 13 | N/A | 0% | 77.59% | Actual planned 34 plau carry forwarded 24 points(total 58 points of which 45 points accepted. And one 13 point story carry forwarded due to code roll back as the changes were causing format and file size issue
16.4 | DEVELOPMENT | 2016_10 | 2016-05-04 | 2016-05-17 | 616 | 47 | 0 | 0 | 47 | 18 | 29 | 0 | 0% | 38.3% | Items carry over due to technical challenge
16.4 | DEVELOPMENT | 2016_11 | 2016-05-18 | 2016-05-31 | 672 | 68 | 0 | 0 | 68 | 68 | 0 | 0 | 0% | 100%
16.5 | DEVELOPMENT | 2016_12 | 2016-06-01 | 2016-06-14 | 644 | 45 | 0 | 0 | 45 | 45 | 0 | 0 |  | 100%
16.5 | DEVELOPMENT | 2016_13 | 2016-06-15 | 2016-06-28 | 672 | 45 | 0 | 0 | 45 | 45 | 0 | 0 | 0% | 100%
Formulas:
Sprint Start Date = [Sprint End Date, row above]+1
Sprint End Date = [Sprint Start Date]+13

## WebPDI
Release Name | Sprint Type | Sprint Number | Sprint Start Date | Sprint End Date | Actual Capacity (in Hrs) | INITIAL VELOCITY PLANNED | Story Points Added | Story Points Removed | FINAL VELOCITY PLANNED | ACTUAL VELOCITY | Story Points Carried Over | Regression Defects with Severity | REQUIREMENTS VOLATILITY (in %) | SPRINT ACCEPTANCE (in %) | Remarks
15.3 | DEVELOPMENT | w2015_14 | 2015-03-18 | 2015-03-31 | 135 | 39 | 0 | 0 | 39 | 39 | 0 | NA | 0% | 100%
15.3 | DEVELOPMENT | w2015_16 | 2015-04-01 | 2015-04-14 | 180 | 27 | 0 | 0 | 27 | 27 | 0 | NA | 0% | 100%
15.3 | DEVELOPMENT | w2015_18 | 2015-04-15 | 2015-04-28 | 162 | 14 | 0 | 0 | 14 | 11 | 3 | NA | 0% | 78.57%
15.3 | DEVELOPMENT | w2015_20 | 2015-04-29 | 2015-05-13 | 153 | 33 | 0 | 0 | 33 | 23 | 10 | NA | 0% | 69.7% | Acceptance Criteria was changed in the middle of sprint
15.3 | DEVELOPMENT | w2015_22 | 2015-05-13 | 2015-05-26 | 180 | 27 | 0 | 0 | 27 | 27 | 0 | NA | 0% | 100% | Clarification on requirements changed
15.3 | DEVELOPMENT | w2015_24 | 2015-05-27 | 2015-06-10 | 180 | 23 | 0 | 0 | 23 | 15 | 8 | NA | 0% | 65.22%
15.3 | DEVELOPMENT | w2015_26 | 2015-06-10 | 2015-06-23 | 180 | 32 | 0 | 0 | 32 | 32 | 0 | NA | 0% | 100% | Change in requirements
15.3 | DEVELOPMENT | w2015_28 | 2015-06-24 | 2015-07-07 | 180 | 24 | 0 | 0 | 24 | 24 | 0 | NA | 0% | 100%
15.3 | DEVELOPMENT | w2015_30 | 2015-07-08 | 2015-07-21 | 162 | 27 | 0 | 0 | 27 | 24 | 0 | NA | 0% | 88.89% | Had Database servers migration issues leading to some data issue for testing
15.3 | DEVELOPMENT | w2015_32 | 2015-07-22 | 2015-08-04 | 220 | 29 | 0 | 18 | 11 | 11 | 0 | NA | -62.07% | 100% | Volatility reason : Testing not completed by Onshore QA
15.3 | DEVELOPMENT | w2015_34 | 2015-08-05 | 2015-08-18 | 171 | 36 | 0 | 0 | 36 | 10 | 26 |  | 0% | 27.78% | Database testing was blocked due to service issues
15.3 | DEVELOPMENT | w2015_36 | 2015-08-19 | 2015-09-01 | 219 | 42 | 0 | 0 | 42 | 21 | 21 |  | 0% | 50% | Database rearch. Is going on
15.3 | DEVELOPMENT | w2015_38 | 2015-09-02 | 2015-09-15 | 180 | 40 | 0 | 0 | 40 | 19 | 21 | NA | 0% | 47.5% | Onshore dependency for DB
15.3 | DEVELOPMENT | w2015_40 | 2015-09-16 | 2015-09-29 | 126 | 35 | 0 | 0 | 35 | 27 | 8 | NA | 0% | 77.14% | Requirement Changes
15.3 | DEVELOPMENT | w2015_42 | 2015-09-30 | 2015-10-13 | 144 | 21 | 0 | 0 | 21 | 3 | 18 | NA | 0% | 14.29% | Estimations were not precise, Change in requirements
15.3 | DEVELOPMENT | w2015_44 | 2015-10-14 | 2015-10-27 | 153 | 31 | 0 | 0 | 31 | 13 | 18 | NA | 0% | 41.94% | Actual hours taken were more than estimated hours due to complexity
15.3 | DEVELOPMENT | w2015_46 | 2015-10-28 | 2015-11-10 | 162 | 18 | 0 | 0 | 18 | 5 | 13 | NA | 0% | 27.78% | Testing was pending
15.3 | DEVELOPMENT | w2015_48 | 2015-11-11 | 2015-11-24 | 162 | 16 | 3 | 0 | 19 | 14 | 5 | NA | 18.75% | 73.68% | Structural Change was required
15.3 | DEVELOPMENT | w2015_50 | 2015-11-25 | 2015-12-08 | 144 | 28 | 3 | 0 | 31 | 18 | 13 | NA | 10.71% | 58.06% | Testing was pending
15.3 | DEVELOPMENT | w2015_52 | 2015-12-09 | 2015-12-22 | 180 | 15 | 0 | 0 | 15 | 15 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | 20160105 | 2015-12-23 | 2016-01-05 | 126 | 24 | 0 | 0 | 24 | 11 | 13 | NA | 0% | 45.83% | Testing dependency
16.1 | DEVELOPMENT | 20160119 | 2016-01-06 | 2016-01-19 | 144 | 25 | 0 | 0 | 25 | 9 | 16 | NA | 0% | 36% | Dependency on database upgradation and IE 11 unavailability
16.1 | DEVELOPMENT | 20160202 | 2016-01-20 | 2016-02-02 | 135 | 56 | 0 | 0 | 56 | 31 | 25 | NA | 0% | 55.36% | Due to database restoration
16.1 | DEVELOPMENT | 20160216 | 2016-02-03 | 2016-02-16 | 162 | 35 | 0 | 0 | 35 | 20 | 15 | NA | 0% | 57.14% | Due to Network access issue, Impediments in stored procedures and pending clarification
16.1 | DEVELOPMENT | 20160301 | 2016-02-17 | 2016-03-01 | 171 | 23 | 11 | 5 | 29 | 18 | 11 | NA | 26.09% | 62.07% | Due to service down and New requirement added to existing bug
16.1 | DEVELOPMENT | 20160315 | 2016-03-02 | 2016-03-15 | 180 | 32 | 13 | 0 | 45 | 40 | 5 | NA | 40.62% | 88.89% | Due to service down.
16.1 | DEVELOPMENT | 20160329 | 2016-03-16 | 2016-03-29 | 144 | 38 | 0 | 0 | 38 | 38 | 0 | NA | 0% | 100%
16.1 | REGRESSION | 20160412 | 2016-03-30 | 2016-04-12 | 162 | 21 | 11 | 2 | 30 | 27 | 3 | NA | 42.86% | 90% | Due to low priority
16.1.1 | DEVELOPMENT | 20160426 | 2016-04-13 | 2016-04-26 | 171 | 41 | 0 | 0 | 41 | 35 | 5 | NA | 0% | 85.37% | Service issue with onsite server
16.2.0 | DEVELOPMENT | 20160510 | 2016-04-27 | 2016-05-10 | 117 | 37 | 0 | 0 | 37 | 27 | 10 | NA | 0% | 72.97% | update regarding the DB changes
16.2.0 | DEVELOPMENT | 20160524 | 2016-05-11 | 2016-05-24 | 180 | 43 | 0 | 0 | 43 | 33 | 13 | NA | 0% | 76.74% | Due to database restoration
16.2.0 | DEVELOPMENT | I20160607 | 2016-05-25 | 2016-06-07 | 171 | 48 | 0 | 0 | 48 | 18 | 30 | NA | 0% | 37.5% | Due to database restoration
16.2.0 | DEVELOPMENT | 20160621 | 2016-06-08 | 2016-06-21 | 180 | 68 | 15 | 0 | 83 | 65 | 18 | NA | 0% | 76.47% | Due to database restoration
16.2.0 | DEVELOPMENT | 20160705 | 2016-06-22 | 2016-07-05 | 171 | 30 | 8 | 0 | 38 | 38 | 0 | NA | 0% | 100%
16.3.0 | DEVELOPMENT | 20160720 | 2016-07-06 | 2016-07-20 | 171 | 32 | 8 | 0 | 40 | 0 | 0 | NA | 0% | 0% | Devolpment completed, Testing pending since Regression Testing going on

## CDM
Release Name | Sprint Type | Sprint Number | Sprint Start Date | Sprint End Date | Actual Capacity (in Hrs) | INITIAL VELOCITY PLANNED | Story Points Added | Story Points Removed | FINAL VELOCITY PLANNED | ACTUAL VELOCITY | Story Points Carried Over | Regression Defects with Severity | REQUIREMENTS VOLATILITY (in %) | SPRINT ACCEPTANCE (in %) | Remarks
3.9.4 | DEVELOPMENT | I2015_10 | 2015-04-28 | 2015-05-11 | 226 | 24 | 0 | 0 | 24 | 20 | 4 | NA | 0% | 83.33% | Complex story took more hours than expected, So didn't get enough time to work on incomplete story.
3.9.4 | DEVELOPMENT | I2010_11 | 2015-05-13 | 2015-05-26 | 324 | 34 | 0 | 0 | 34 | 26 | 8 | NA | 0% | 76.47% | 1. Technical Challenge 2. New surprise issue arised while testing
3.9.4 | DEVELOPMENT | I2015_12 | 2015-05-27 | 2015-06-10 | 297 | 40 | 0 | 0 | 40 | 36 | 4 | NA | 0% | 90% | Complex and an extjs bug
3.9.4 | DEVELOPMENT | I2015_13 | 2015-06-10 | 2015-06-23 | 342 | 52 |  |  | 52 | 44 | 8 | NA | 0% | 84.62% | Due to Technical Complexity US was moved
3.9.4 | DEVELOPMENT | I2015_14 | 2015-06-24 | 2015-07-08 | 342 | 50 | 0 | 0 | 50 | 50 | 0 | NA | 0% | 100%
3.9.4 | DEVELOPMENT | I2015_15 | 2015-07-08 | 2015-07-21 | 332 | 62 | 0 | 0 | 62 | 62 | 0 | NA | 0% | 100%
3.9.4 | DEVELOPMENT | I2015_16 | 2015-07-22 | 2015-08-04 | 351 | 52 | 0 | 8 | 44 | 44 | 6 | NA | -15.38% | 100%
3.9.4 | REGRESSION | I2015_17 | 2015-08-05 | 2015-08-18 | 351 | 34 | 0 | 0 | 34 | 34 | 0 | 1 - Medium | 0% | 100% | Some defects are prioritized
3.9.4 | DEPLOYMENT | I2015_18 | 2015-08-19 | 2015-09-01 | 351 | 46 | 0 | 0 | 46 | 46 | 0 | NA | 0% | 100% | Release went well Zero defects
3.9.4 | DEVELOPMENT | I2015_19 | 2015-09-02 | 2015-09-15 | 360 | 48 | 0 | 0 | 48 | 48 | 0 | NA | 0% | 100%
3.9.4 | DEVELOPMENT | I2015_20 | 2015-09-16 | 2015-09-29 | 279 | 38 | 0 | 0 | 38 | 36 | 2 | NA | 0% | 94.74% | Dependency blockage on product analyst
3.9.4 | DEVELOPMENT | I2015_21 | 2015-09-30 | 2015-10-13 | 369 | 42 | 0 | 0 | 42 | 42 | 0 | NA | 0% | 100%
3.9.4 | DEVELOPMENT | I2015_22 | 2015-10-14 | 2015-10-27 | 306 | 32 | 0 | 0 | 32 | 32 | 0 | NA | 0% | 100%
3.9.4 | DEVELOPMENT | I2015_23 | 2015-10-28 | 2015-11-10 | 252 | 32 | 4 | 0 | 36 | 20 | 16 | NA | 12.5% | 55.56% | One user story was not replicable in the dev enviornment, More priority was given to one of the story
3.9.4 | REGRESSION | I2015_24 | 2015-11-11 | 2015-11-24 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | NA | #DIV/0! | #DIV/0! | Planning did not happen

## ContentLegacy
Release Name | Sprint Type | Sprint Number | Sprint Start Date | Sprint End Date | Actual Capacity (in Hrs) | INITIAL VELOCITY PLANNED | Story Points Added | Story Points Removed | FINAL VELOCITY PLANNED | ACTUAL VELOCITY | Story Points Carried Over | Regression Defects with Severity | REQUIREMENTS VOLATILITY (in %) | SPRINT ACCEPTANCE (in %) | Remarks
2.9 | DEVELOPMENT | I2015_10 | 2015-04-30 | 2015-05-13 | 386 | 46 | 0 | 0 | 46 | 46 | 0 | NA | 0% | 100%
2.9 | DEVELOPMENT | I2010_11 | 2015-05-14 | 2015-05-27 | 440 | 32 | 0 | 0 | 32 | 28 | 4 | NA | 0% | 87.5% | Dependency with ICS team
2.9 | DEVELOPMENT | I2015_12 | 2015-05-27 | 2015-06-10 | 431 | 36 | 0 | 0 | 36 | 20 | 16 | NA | 0% | 55.56% | New framework(Visual Studio 2013) is not installed on VDI machine so could not finish code upgrade task
2.9 | DEVELOPMENT | I2015_13 | 2015-06-11 | 2015-06-24 | 422 | 62 | 0 | 0 | 62 | 54 | 8 | NA | 0% | 87.1% | Dependency with IT Team
2.9 | DEVELOPMENT | I2015_14 | 2015-06-25 | 2015-07-09 | 332 | 38 | 0 | 0 | 38 | 38 | 0 | NA | 0% | 100%
2.9 | DEVELOPMENT | I2015_15 | 2015-07-09 | 2015-07-22 | 332 | 48 | 0 | 0 | 48 | 32 | 16 | NA | 0% | 66.67% | There was issue with DEV server
2.9 | DEVELOPMENT | I2015_16 | 2015-07-23 | 2015-08-05 | 404 | 44 | 0 | 0 | 44 | 32 | 12 | NA | 0% | 72.73% | Onshore Developer did not complete one US due to technical complexity
2.9 | REGRESSION | I2015_17 | 2015-08-06 | 2015-08-19 | 431 | 57 | 0 | 0 | 57 | 37 | 20 | High - 3; Medium - 1; Low - 3; | 0% | 64.91%
2.9 | DEPLOYMENT | I2015_18 | 2015-08-20 | 2015-09-02 | 377 | 47 | 0 | 0 | 47 | 41 | 6 |  | 0% | 87.23% | Dependency on Network team
2.9 | DEVELOPMENT | I2015_19 | 2015-09-03 | 2015-09-16 | 422 | 40 | 0 | 0 | 40 | 28 | 12 | NA | 0% | 70%
2.9 | DEVELOPMENT | I2015_20 | 2015-09-17 | 2015-09-30 | 323 | 54 | 0 | 0 | 54 | 40 | 14 | NA | 0% | 74.07% | Due to the Complexity of the module
2.9 | DEVELOPMENT | I2015_21 | 2015-10-01 | 2015-10-14 | 377 | 40 | 0 | 0 | 40 | 40 | 0 | NA | 0% | 100%
2.9 | DEVELOPMENT | I2015_22 | 2015-10-15 | 2015-10-28 | 225 | 19 | 6 | 3 | 22 | 22 | 0 | NA | 15.79% | 100% | Due to unplanned events within the team, moved the items to next iteration
2.9 | DEVELOPMENT | I2015_23 | 2015-10-29 | 2015-11-11 | 288 | 10 | 0 | 0 | 10 | 10 | 0 | NA | 0% | 100% | CNS deployment and validation on non production environment
2.9 | REGRESSION | I2015_24 | 2015-11-12 | 2015-11-25 | 312 | 44 | 12 | 0 | 56 | 52 | 4 | NA | 27.27% | 92.86% | Due to unplanned leave
2.9 | REGRESSION | I2015_25 | 2015-11-26 | 2015-12-09 | 296 | 40 | 12 | 0 | 52 | 46 | 6 | NA | 30% | 88.46% | As Production deployment scheduled on weekend
2.9 | DEVELOPMENT | I2015_26 | 2015-12-10 | 2016-01-06 | 456 | 50 | 0 | 0 | 50 | 50 | 0 | NA | 0% | 100%
15.3.1 | DEVELOPMENT | I2016_01 | 2016-01-07 | 2016-01-20 | 216 | 20 | 0 | 0 | 20 | 20 | 0 | NA | 0% | 100%
15.3.1 | DEVELOPMENT | I2016_02 | 2016-01-21 | 2016-02-03 | 192 | 30 | 0 | 0 | 30 | 30 | 0 | NA | 0% | 100%
16.1.0 | DEVELOPMENT | I2016_03 | 2016-02-04 | 2016-02-17 | 216 | 24 | 0 | 0 | 24 | 24 | 0 | NA | 0% | 100%
16.1.0 | DEVELOPMENT | I2016_04 | 2016-02-18 | 2016-03-02 | 232 | 24 | 0 | 0 | 24 | 24 | 0 | NA | 0% | 100%
16.1.0 | REGRESSION | I2016_05 | 2016-03-03 | 2016-03-30 | 416 | 46 | 0 | 0 | 46 | 46 | 0 | NA | 0% | 100%
16.1.0 | REGRESSION | I2016_05 | 2016-03-03 | 2016-03-30 | 416 | 46 | 0 | 0 | 46 | 46 | 0 | NA | 0% | 100%
16.1.0 | DEVELOPMENT | I2016_06 | 2016-04-04 | 2016-04-13 | 224 | 20 | 0 | 0 | 20 | 20 | 0 | NA | 0% | 100%
16.1.1 | DEVELOPMENT | I2016_07 | 2016-04-14 | 2016-04-27 | 112 | 12 | 0 | 0 | 12 | 8 | 4 | NA | 0% | 66.67% | MDM transition did not happen , waiting for management approval
16.2.0 | DEVELOPMENT | I2016_08 | 2016-04-28 | 2016-05-11 | 160 | 16 | 0 | 0 | 12 | 8 | 4 | NA | 0% | 66.67% | MDM transition did not happen , waiting for management approval
16.2.0 | DEVELOPMENT | I2016_09 | 2016-05-12 | 2016-05-31 | 184 | 16 | 0 | 0 | 16 | 0 | 0 | NA | 0% | 100%

## KS
Release Name | Sprint Type | Sprint Number | Sprint Start Date | Sprint End Date | Actual Capacity (in Hrs) | INITIAL VELOCITY PLANNED | Story Points Added | Story Points Removed | FINAL VELOCITY PLANNED | ACTUAL VELOCITY | Story Points Carried Over | Regression Defects with Severity | REQUIREMENTS VOLATILITY (in %) | SPRINT ACCEPTANCE (in %) | Remarks
4.9.9 | DEVELOPMENT | I2015_10 | 2015-04-29 | 2015-05-13 | 252 | 38 | 0 | 0 | 38 | 30 | 8 | NA | 0% | 78.95% | Need more discussion
4.9.9 | DEVELOPMENT | I2015_11 | 2015-05-13 | 2015-05-26 | 324 | 35 | 0 | 0 | 35 | 27 | 8 | NA | 0% | 77.14% | 1. Complexity + more enhancement
4.9.9 | DEVELOPMENT | I2015_12 | 2015-05-26 | 2015-06-09 | 360 | 44 | 0 | 0 | 44 | 44 | 0 | NA | 0% | 100%
4.9.9 | DEVELOPMENT | I2015_13 | 2015-06-10 | 2015-06-23 | 333 | 48 | 0 | 0 | 48 | 40 | 8 | NA | 0% | 83.33% | Due to Technical Complexity US was moved
4.9.9 | DEVELOPMENT | I2015_15 | 2015-07-08 | 2015-07-21 | 315 | 34 | 8 | 0 | 42 | 30 | 12 | NA | 23.53% | 71.43% | Due to unplanned PTO and technical complexity US was moved
4.9.9 | DEVELOPMENT | I2015_16 | 2015-07-21 | 2015-08-04 | 351 | 48 | 5 | 8 | 45 | 45 | 0 | NA | -6.25% | 100%
4.9.9 | REGRESSION | I2015_17 | 2015-08-05 | 2015-08-18 | 360 | 41 | 4 | 0 | 45 | 45 | 0 | 0 | 9.756% | 100%
4.9.9 | DEPLOYMENT | I2015_18 | 2015-08-19 | 2015-09-01 | 324 | 29 | 0 | 0 | 29 | 17 | 12 |  | 0% | 58.62% | Acceptance Critrea not met
4.9.9 | DEVELOPMENT | I2015_19 | 2015-09-02 | 2015-09-15 | 288 | 32 | 0 | 0 | 32 | 32 | 0 | NA | 0% | 100%
4.9.9 | DEVELOPMENT | I2015_20 | 2015-09-16 | 2015-09-29 | 225 | 32 | 0 | 0 | 32 | 32 | 0 | NA | 0% | 100%
4.9.9 | DEVELOPMENT | I2015_21 | 2015-09-30 | 2015-10-13 | 262.5 | 30 | 12 | 8 | 34 | 34 | 0 | NA | 13.33% | 100%
4.9.9 | DEVELOPMENT | I2015_22 | 2015-10-14 | 2015-10-27 | 240 | 29 | 6 | 0 | 35 | 35 | 0 | NA | 20.69% | 100%
4.9.9 | DEVELOPMENT | I2015_23 | 2015-10-28 | 2015-11-10 | 217.5 | 28 | 2 | 0 | 30 | 30 | 0 | NA | 7.143% | 100%
4.9.9 | REGRESSION | I2015_24 | 2015-11-11 | 2015-11-24 | 210 | 28 | 0 | 2 | 26 | 26 | 0 | NA | -7.143% | 100% | One Test Case Failed Due to Firewall Issue
4.9.9 | DEVELOPMENT | I2015_25 | 2015-11-25 | 2015-12-08 | 270 | 34 | 6 | 0 | 40 | 40 | 0 | NA | 17.65% | 100%
4.9.10 | DEVELOPMENT | I2015_26 | 2015-12-09 | 2015-12-22 | 277.5 | 27 | 0 | 0 | 27 | 27 | 0 | NA | 0% | 100%
4.9.10 | DEVELOPMENT | I2016_01 | 2015-12-23 | 2016-01-05 | 187.5 | 36 | 0 | 0 | 36 | 36 | 0 | NA | 0% | 100%
4.9.10 | DEVELOPMENT | I2016_02 | 2016-01-06 | 2016-01-19 | 232.5 | 34 | 0 | 0 | 34 | 34 | 0 | NA | 0% | 100%
4.9.10.1 | DEVELOPMENT | I2016_03 | 2016-01-20 | 2016-02-02 | 262.5 | 36 | 0 | 0 | 36 | 28 | 8 | NA | 0% | 77.78% | Due to change of scope at last moment
4.9.10.2 | DEVELOPMENT | I2016_04 | 2016-02-03 | 2016-02-16 | 285 | 42 | 0 | 0 | 42 | 42 | 0 | NA | 0% | 100%
4.9.10.2 | DEVELOPMENT | I2016_05 | 2016-02-17 | 2016-03-01 | 277.5 | 48 | 0 | 0 | 48 | 48 | 0 | NA | 0% | 100%
4.9.10.2 | REGRESSION | I2016_06 | 2016-03-02 | 2016-03-15 | 270 | 45 | 0 | 8 | 37 | 37 | 0 | NA | -17.78% | 100%
16.1 | DEPLOYMENT | I2016_07 | 2016-03-16 | 2016-03-29 | 262.5 | 50 | 0 | 0 | 50 | 50 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | I2016_08 | 2016-03-30 | 2016-04-13 | 232.5 | 39 | 0 | 0 | 39 | 31 | 8 | NA | 0% | 79.49% | Application was down for 1 day due to Database refresh
16.1 | DEVELOPMENT | I2016_09 | 2016-04-14 | 2016-04-26 | 245 | 47 | 0 | 0 | 47 | 47 | 0 | NA | 0% | 100%
16.2 | DEVELOPMENT | I2016_10 | 2016-04-27 | 2016-05-10 | 292.5 | 48 | 8 | 0 | 56 | 48 | 8 | NA | 16.67% | 85.71% | Eclipse crashed two times on two different dates and lost chunk of code from two different files which caused the delay

## Reporting
Release Name | Sprint Type | Sprint Number | Sprint Start Date | Sprint End Date | Actual Capacity (in Hrs) | INITIAL VELOCITY PLANNED | Story Points Added | Story Points Removed | FINAL VELOCITY PLANNED | ACTUAL VELOCITY | Story Points Carried Over | Regression Defects with Severity | REQUIREMENTS VOLATILITY (in %) | SPRINT ACCEPTANCE (in %) | Remarks
15.3 | DEVELOPMENT | I2015_06 | 2015-03-20 | 2015-04-02 | 346 | 45 | 0 | 0 | 45 | 45 | 0 | NA | 0% | 100%
15.3 | DEVELOPMENT | I2015_07 | 2015-04-02 | 2015-04-15 | 339 | 43 | 0 | 0 | 43 | 43 | 0 | NA | 0% | 100%
15.3 | DEVELOPMENT | I2015_08 | 2015-04-16 | 2015-04-29 | 284 | 40 | 3 | 0 | 43 | 40 | 3 | NA | 7.5% | 93.02% | US40303: New US added and Prioritized
15.3 | DEVELOPMENT | I2017_09 | 2015-05-01 | 2015-05-15 | 282 | 44 | 0 | 0 | 44 | 44 | 0 | NA | 0% | 100%
15.3 | DEVELOPMENT | I2010_10 | 2015-05-14 | 2015-05-27 | 491 | 51 | 3 | 0 | 54 | 49 | 5 | NA | 5.882% | 90.74% | Unit Testing fails
15.3 | DEVELOPMENT | I2015_11 | 2015-05-29 | 2015-06-12 | 491 | 62 | 8 | 0 | 70 | 70 | 0 | NA | 12.9% | 100%
15.3 | REGRESSION | I2015_12 | 2015-06-11 | 2015-06-24 | 436 | 57 | 0 | 0 | 57 | 52 | 5 | High 11; Medium 9; Low 17; | 0% | 91.23% | Some other US was prioritized
15.3 | DEPLOYMENT | I2015_13 | 2015-06-25 | 2015-07-09 | 366 | 55 | 0 | 0 | 55 | 55 | 0 | 0 | 0% | 100% | Some other US was prioritized
15.4 | DEVELOPMENT | I2015_14 | 2015-07-09 | 2015-07-22 | 364 | 47 | 8 | 0 | 55 | 55 | 0 | NA | 17.02% | 100%
15.4 | DEVELOPMENT | I2015_15 | 2015-07-23 | 2015-08-05 | 453 | 61 | 0 | 0 | 61 | 61 | 0 | NA | 0% | 100%
15.4 | DEVELOPMENT | I2015_16 | 2015-08-06 | 2015-08-19 | 494 | 72 | 3 | 0 | 75 | 75 | 5 | NA | 4.167% | 100% | Inline defect pending for testing
15.4 | DEVELOPMENT | I2015_17 | 2015-08-20 | 2015-09-02 | 493 | 65 | 0 | 0 | 65 | 65 | 0 | NA | 0% | 100%
15.4 | DEVELOPMENT | I2015_18 | 2015-09-03 | 2015-09-16 | 400 | 47 | 0 | 0 | 47 | 29 | 18 | NA | 0% | 61.7%
15.4 | DEVELOPMENT | I2015_19 | 2015-09-17 | 2015-09-30 | 336 | 50 | 0 | 0 | 50 | 50 | 0 | NA | 0% | 100%
15.4 | REGRESSION | I2015_20 | 2015-10-01 | 2015-10-14 | 224 | 60 | 0 | 0 | 60 | 60 | 0 | Medium - 2; Low - 1; | 0% | 100%
15.4 | DEPLOYMENT | I2015_21 | 2015-10-15 | 2015-10-28 | 441 | 58 | 0 | 0 | 58 | 58 | 0 | NA | 0% | 100%
15.4 | DEVELOPMENT | I2015_22 | 2015-10-29 | 2015-11-12 | 175 | 59 | 0 | 0 | 59 | 59 | 0 | NA | 0% | 100%
15.4 | DEVELOPMENT | I2015_23 | 2015-11-12 | 2015-11-25 | 175 | 52 | 0 | 0 | 52 | 49 | 3 | NA | 0% | 94.23% | Framework Issue
15.4 | DEVELOPMENT | I2015_24 | 2015-11-26 | 2015-12-09 | 210 | 47 | 0 | 0 | 47 | 47 | 0 | NA | 0% | 100%
15.4 | DEVELOPMENT | I2015_25 | 2015-12-11 | 2015-12-24 | 126 | 42 | 0 | 0 | 42 | 42 | 0 | NA | 0% | 100%
15.4 | DEVELOPMENT | I2015_26 | 2015-12-25 | 2016-01-07 | 161 | 36 | 0 | 0 | 36 | 36 | 0 | NA | 0% | 100%
16.1 | DEVELOPMENT | I2016_01 | 2016-01-08 | 2016-01-21 | 196 | 57 | 3 | 0 | 60 | 60 | 0 | NA | 5.263% | 100%
16.1 | DEVELOPMENT | I2016_02 | 2016-01-22 | 2016-02-04 | 168 | 43 | 0 | 0 | 43 | 43 | 0 | NA | 0% | 100%
16.1 | REGRESSION | I2016_03 | 2016-02-05 | 2016-02-18 | 154 | 45 | 0 | 0 | 45 | 45 | 0 | NA | 0% | 100%
16.1 | DEPLOYMENT | I2016_04 | 2016-02-19 | 2016-03-03 | 182 | 34 | 0 | 0 | 34 | 34 | 0 | NA | 0% | 100%
16.2 | DEVELOPMENT | I2016_05 | 2016-03-04 | 2016-03-17 | 196 | 55 | 0 | 0 | 55 | 55 | 0 | NA | 0% | 100%
16.2 | DEVELOPMENT | I2016_06 | 2016-03-18 | 2016-03-31 | 252 | 51 | 0 | 8 | 43 | 43 | 0 | NA | -15.69% | 100%
16.2 | DEVELOPMENT | I2016_07 | 2016-04-01 | 2016-04-14 | 322 | 43 | 0 | 0 | 43 | 43 | 0 | NA | 0% | 100%
16.2 | DEVELOPMENT | I2016_08 | 2016-04-15 | 2016-04-28 | 273 | 45 | 23 | 8 | 60 | 60 | 0 | NA | 33.33% | 100%
16.2 | DEVELOPMENT | I2016_09 | 2016-04-29 | 2016-05-12 | 322 | 49 | 28 | 18 | 59 | 59 | 0 | NA | 20.41% | 100%
16.2 | DEVELOPMENT | I2016_10 | 2016-05-13 | 2016-05-26 | 329 | 48 | 26 | 15 | 59 | 59 | 0 | NA | 22.92% | 100%
16.2 | DEVELOPMENT | I2016_11 | 2016-05-27 | 2016-06-09 | 322 | 44 | 11 | 8 | 47 | 47 | 0 | NA | 6.818% | 100%
16.2 | DEVELOPMENT | I2016_12 | 2016-06-10 | 2016-06-23 | 315 | 35 | 0 | 0 | 35 | 35 | 0 | NA | 0% | 100%
16.2 | DEVELOPMENT | I2016_13 | 2016-06-24 | 2016-07-07 | 308 | 42 | 0 | 0 | 42 | 42 | 0 | NA | 0% | 100%
16.3 | DEVELOPMENT | I2016_14 | 2016-07-08 | 2016-07-21 | 322 | 42 | 5 | 10 | 37 | 37 | 0 | NA | -11.9% | 100%